## Status
Project Progress Review
Project Name: | Project J31 | Project Lead: | Jon Boy | Date: | 2012-11-23
Attendees: N/A: e-mail status this week
Effort / Schedule: See Weekly Project Schedule Updates
Project accomplishments this reporting period: EFB / Charts The graphics configuration files for Project J31 at PHX were installed in the Config/J31 directory. Project Configuration Files A J31 repository under the B757Atd1 directory was established, and simulation configuration files (siminit, initial conditions, ACARS company route files, graphics configuration) were installed. TCAS No software development was completed this week; no further development on the module or interface can be done until the delivery of the new TcasModule. Started enhancements to the test configuration software. Started audio alert testing at a console in the real-time room. Winds Inactive this week. Distributed Simulation Work is underway for modifying the LaSRS++ distributed simulation capability to support both ADS-B and non-ADS-B equipped aircraft in a scenario (for all previous projects, all traffic was sending ADS-B data). The DistributedSimPlayback utility was updated to suppress ADS-B interactions, so that existing scenario playback files can be used to test the new capability. (This work needs to be completed prior to recording a new scenario with ATOL, which is currently scheduled for early December.) Flat Database Tom Wolters received a rough estimate of $9k to add compound sloping to the Phoenix Airport. Researcher Evaluation A researcher checkout session was supported on Thursday, 11/15/2012 in the DTS. In attendance were Baxley, Britton, Otero, and Shay. * Baxley tested ACARS routes. All ILS approaches for KOOLY and EAGUL arrivals tested successfully. MAIER-FIVE arrivals had to be conected to ILS approaches through additional data link syntax, and was completed during this sesssion. Further work will be done to route around the restricted airspace. * The extended runway centerline on the navigation display was correct during the session. B. Hutchinson noted that when the arrival and departure airport in the FMC are the same, the runway centerline can show on the wrong runway. Today was the first time we were using the company routes with different arrival/departure airports. This issue has been closed.
Milestone Accomplishments:
Kickoff Meeting - Planned Date: 10/30/2012 Actual Completion Date: 10/30/2012
Other Milestones : Planned Date Actual Completion Delivery: TCAS black box and wrapper- 11/16/2012 MM/DD/YYYY Delivery: ASTAR route files 11/30/2012 MM/DD/YYYY Delivery: FMS Database update 11/15/2012 MM/DD/YYYY Delivery: PHX charts for EFB 12/10/2012 MM/DD/YYYY Delivery: GRIB2 wind files 11/26/2012 11/01/2012
Production Readiness Review - Planned Date: MM/DD/YYYY Actual Completion Date: MM/DD/YYYY
Project Training: There is no project specific training identified in the SPMP and/or the project schedule. There is no planned training required for the project.
Data Management: * Weekly status updates (risk workbook + copy of schedule) stored in project repository * Requirements baseline audit conducted; audit report stored in project repository
Project Commitments:
Stakeholder Involvement: No issues relating to stakeholder involvement were identified this reporting period.
Project Issues Review: See Issues tab for details.
| Open Issues = | 1
| Closed Issues = | 1
| Total Issues = | 2
Status of Issues discussed during meeting and required actions: Summarize the current status of issues and actions taken. Indicate that there were nn new issues identified this reporting period, or that there were no new issues identified during this reporting period.
Project Risk Review: See Risks Tab for details.
| Open Risks = | 9
| Closed Risks = | 2
| Total Risks = | 11
Status of Risks discussed during meeting and required actions: Summarize the current status of risks and actions taken. Indicate that there were nn new risks identified this reporting period, or that there were no new risks identified this reporting period.

## Issues
Project Issues Management Log
Project Name: | Project J31 |  |  | Project Lead: | Jon Boy | Date: | 2012-11-23
Issue No. | Date Identified | Issue or Action Summary | Action Assigned to | Due Date | Notes and Corrective Action | Status | Date Closed
1 | 2012-11-02 | DTS Navigation display was showing runway centerline and dashed extension line for the wrong runway on approaches to both 25L and 26. | M. Hill | 2012-12-21 | 11/09/2012: We saw this error again on 11/08, although it was on the correct runway for at least one run. The extended centerline info comes from the FMC. This will be researched next week. 11/15/2012: centerline is correct in session 11/15. B. Hutchinson mentioned that when the departure and arrival airport is the same, the centerline can be incorrect. 11/15 was the first day we were using the company routes, so dep/arr airports were different, and centerline looks good. | Closed | 2012-11-15
2 | 2012-11-16 | Delivery of TCAS black box and wrapper is delayed (arbitrarily scheduled for 11/16). Development work cannot proceed until we have the software. | M. Hill | 2012-11-30 |  | Open
3
4
5
6
7
8
9
10
11
12
13
14
15
To add a new issue row, <Tab> past the 'Date Closed' column of the last row. Do not insert or delete rows in the table; doing so will break automated issue numbering.
Issue Summary
|  |  | Open | Issues = | 1
|  |  | Closed | Issues = | 1
|  |  | Total | Issues = | 2
These numbers are transferred to the Status Tab
Note on D22: The Issue Summary is computed and transferred to the Status Tab.

## Risks
| Project Risk Matrix | [11 empty] | Consequence Values | Likelihood Values
Project Name: | Project J31 |  |  |  | Project Lead: | Jon Boy |  |  |  |  | Date: | 2012-11-23 | I - Catastrophic | A - Likely to occur immediately
Risk ID No. | Risk Description | Consequence | Likelihood | Risk Level | Risk Owner | Date Identified | Column1 | Column2 | Column3 | Risk Status | Status | Date Closed | II - Critical | B - Probably will occur in time
1 | Delivery of TCAS black box and wrapper is delayed (delivery date is unknown) | II - Critical | C - May occur | Medium | M. Hill | 2012-10-12 |  |  |  | Closed, and moved to an issue. | Closed | 2012-11-16 | III - Moderate | C - May occur
2 | Delivery of FMS database is delayed | II - Critical | E - Improbable | Low | M. Hill | 2012-10-12 |  |  |  |  | Open |  | IV - Negligible | D - Unlikely to occur
3 | Delivery of ASTAR route files is delayed (delivery date is unknown) | III - Moderate | D - Unlikely to occur | Medium | M. Hill | 2012-10-12 |  |  |  | 11/01/2012 risk consequence and likelihood reduced; since J31 has no custom waypoints, we can generate these files in-house (I think) if we need to | Open |  | V - No Impact | E - Improbable
4 | Delivery of PHX charts for the EFB is delayed (delivery date is unknown) | IV - Negligible | C - May occur | Low | M. Hill | 2012-10-12 |  |  |  | 10/31/2012: Reduced this risk from critical to negligible. Downloaded RNAV RNP charts for PHX from AirNav.com; can start development work with these. | Open
5 | Delivery of GRIB2 wind files is delayed (delivery date is unknown) | II - Critical | C - May occur | Medium | M. Hill | 2012-10-12 |  |  |  | Files received 11/01/2012 | Closed | 2012-11-01
6 | FMC database will only be installed on FMC3 to prevent interference with other production jobs. If FMC3 fails, the hot spare will need to be swapped in. | IV - Negligible | D - Unlikely to occur | Low | M. Hill | 2012-10-25 |  |  |  |  | Open
7 | Scenario playback file cannot be recorded w/ ATOL until January 2013 | IV - Negligible | C - May occur | Low | M. Hill | 2012-10-25 |  |  |  | 10/30/2012: recorded scenarios from IM-NOVA can be used for testing in the interim. | Open
8 | The visual database is flat at KPHX (all threshold elevations are 1111, rather than 1135, 1134, 1126). This might be unacceptable for the experiment | III - Moderate | D - Unlikely to occur | Medium | M. Hill | 2012-10-22 |  |  |  | 10/30/2012: Sent runway threshold info to Tom Wolters; he will talk with the database developer about correcting them. 11/16/2012: Wolters received a rough estimate of $9k to add compound sloping to the runways. | Open
9 | LaSRS++ TrafficSimulation is not ready for recording ATOL scenario scheduled for Dec. 5, 2012. (TrafficSim does not currently support non-FIM aircraft) | III - Moderate | C - May occur | Medium | M. Hill | 2012-10-26 |  |  |  | 10/30/2012: fixed a typo in the date from Nov. 5 to Dec. 5. | Open
10 | Converting from GRIB2 wind file format to LaSRS++ compatible format takes longer than planned | II - Critical | D - Unlikely to occur | Medium | M. Hill | 2012-10-26 |  |  |  | 10/30/2012: We can potentially mitigate this risk by getting a sample GRIB2 file. 11/09/2012: We have received a sample 13km grid file. C-library for decoding GRIB2 was successfully installed and used w/ a driver program for examining the contents of the file(s). | Open
11 | EFB vector graph requirement is an implementation detail that may not be compatible with EFB software/hardware. | II - Critical | C - May occur | Medium | M. Hill | 2012-10-26 |  |  |  |  | Open
12
13
14
15
16
To add a new issue row, <Tab> past the 'Date Closed' column of the last row. Do not insert or delete rows in the table; doing so will break automated issue numbering.
Risk Summary
[5 empty] | Open | Risks = | Issues = | 0 |  | 9
[5 empty] | Closed | Risks = | Issues = | 0 |  | 2
[5 empty] | Total | Risks = | Issues = | 0 |  | 11
These numbers are transferred to the Status Tab
Note on F22: The Risk Summary is computed and transferred to the Status Tab.

## Definitions
Consequence Level Descriptions: | Likelihood Definitions:
Use the following definitions based on NPR 8000.4 to determine the consequence level. | Use the following definitions to communicate the risk likelihood.
a. Class I - Catastrophic. A condition that may cause: 1) death or permanently disabling injury; 2) facility destruction, or loss of crew, major systems, or vehicle during the mission; or 3) schedule slippage causing a schedule overrun greater than 50 percent of the original schedule. | A - Likely to occur immediately (e.g., probability > 0.1)
b. Class II - Critical. A condition that may cause: 1) severe injury or occupational illness; 2) major property damage to facilities, systems, equipment; or 3) schedule slippage causing a schedule overrun between 15 percent and not exceeding 50 percent of the original schedule. | B - Probably will occur in time (e.g., 0.1 > probability > 0.01).
c. Class III - Moderate. A condition that may cause: 1) minor injury or occupational illness; 2) minor property damage to facilities, systems, equipment; or 3) internal schedule slip that does not impact delivery date or schedule overrun between 2 percent and not exceeding 15 percent of original schedule. | C - May occur in time (e.g., 0.01 > probability > 0.001)
d. Class IV - Negligible. A condition that could cause: 1) the need for minor first aid treatment but would not adversely affect personal safety or health; 2) damage to facilities, equipment at more than normal wear and tear level; or 3) internal schedule slip that does not impact internal development milestones or schedule overrun less than 2 percent of original schedule. | D - Unlikely to occur (e.g., 0.001 > probability > 0.000001)
e. Class V - No Impact. | E – Improbable to occur (e.g., 0.000001 > probability).

## File Naming
Project Workbook
| Status | Issues | Risks | Revision History
| Tab 1 | Tab 2 | Tab 3 | Tab 4
Wk 1 | Filename: Project A01_Status_20110803
Wk 2 | Filename: Project A01_Status_20110810
Wk 3 | Filename: Project A01_Status_20110817
Wk 4 | Filename: Project A01_Status_20110826
Project A01 = Your Project Number
Status = Type of report
YYYYMMDD = Date of Report

## Revision History
Revision History of Project Workbook Template
Date | Revision | Description | Implementer | Approval
2011-08-24 | 1.0 | Initial Version | TV | LCK
2011-09-20 | 1.1 | Added Revision History worksheet Status Worksheet - Added Attendees List - Removed process audit status - Changed date placeholders to MM/DD/YYYY format - Changed 'Researcher Acceptance' to 'Production Readiness Review' Issues Worksheet - Made 'Corrective Action' a single column rather than merged columns. This required moving the issues summary and the status date. - Ensured that all columns had the same default format. - Added instructions to last issue row for adding new issue rows. - Made status of issue a drop down list selection - Added auto filters to columns for issues list Risk Worksheet - Made 'Risk Status' a single column rather than merged columns. This required moving the risk summary and the status date. - Ensured that all columns had the same default format. - Added instructions to last issue row for adding new issue rows. - Made consequence, likelihood, risk level, and status of risk into drop down list selections - Added auto filters to columns for risk list File Naming Worksheet - Removed 'Requirements' from description of worksheet tabs | MMM
2011-09-21 | 1.2 | Set print areas on all worksheets so that the width of each worksheet fits on one page. Status Worksheet - Expanded width of report so that Production Readiness Review status fits on one line - Corrected formula for total number of risks Risk Worksheet - Changed format of 'Risk Status' cells to General from Custom in order to allow for autofiltering. File Naming - Added entry for Revision History tab to table | MMM
2011-11-03 | 1.3 | New definitions worksheet containing definitions for consequence and likelihood levels. Issues Worksheet - Added automated number of issues - Added help text to header row of table - Added conditional formatting to automatically make the background of closed issues grey. - Changed name of 'Date' column to 'Date Closed' column - Changed name of 'Issue Description' to 'Issue or Action Summary' - Changed name of 'Corrective Action Taken/Notes' to 'Notes and Corrective Action' - Modified example issue. - Added directions for expanding issues list. Risks Worksheet - Added automated number of risks - Added help text to header row of table - Added conditional formatting to automatically make the background of closed risks grey. - Added automatic computation of risk level based on consequence and likelihood. Also made cells conditionally formatted based on risk level for open risks. (Closed risks are formatted as described above.) Cell background is red for High risk level, yellow for Medium risk level, and green for Low risk level. - Changed drop down list for consequence and likelihood to include the text summary for each consequence or risk level, respectively. - Moved data description in header for Risk Status column to the help text. - Removed, from the header text, the parenthetical reminders of the level identifiers for the consequence, likelihood, and risk level fields. The level identifiers appear in the help text. - Changed text format of consequence, likelihood, and risk level fields from vertical text to horizontal text. The drop down lists do not display the full text of choices unless the column is wide enough to show it. - Changed 'Date' column to 'Date Closed' column. - Modified example risk. - Added directions for expanding risk matrix. | MMM
2011-11-28 | 1.4 | Minor spelling errors corrected on all sheets. Risk Worksheet - Text for likelihood drop-down options A & B modified to make their relative probabilities clearer | MMM | LCK